## Summary1 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT - SUMMARY
APRIL 2008
DRAFT
|  | DISTRICT FUNDING |  |  | PROJECTIONS |  | OTHER 2001 BOND FUNDING |  |  |  | 2006 BOND FUNDING |  |  | TOTAL BOND FUNDING
DESCRIPTION |  | Total Allocated | Total Cost To Date | Balance | $ Estimate to Complete | Funding Needed | Total Allocated | Total Cost To Date | Balance |  | Total Allocated | Total Cost To Date | Balance | Total Allocated | Total Cost To Date | Balance
DISTRICT 1 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRICT 2 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRICT 3 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRICT 4 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRICT 5 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRICT 6 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRICT 7 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COUNTY-WIDE 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2001 PARK BOND TOTAL

## Summary (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT - SUMMARY
APRIL 2008
DRAFT
|  | 2001 PARK BOND |  |  | PROJECTIONS |  | OTHER BOND FUNDING
|  | FUNDED | ALLOCATED | AVAILABLE | $ Estimate to Complete | Funding Needed | 2001 Other District(s) | 2001 CountyWide | 2005 Bond Fund | Interest Funding | Other | Total Funding
DISTRICT 1 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DISTRICT 2 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DISTRICT 3 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DISTRICT 4 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DISTRICT 5 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DIST. 1 - 5 CROSS-DISTRICTS |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
TOTAL DIST 1 - 5 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DISTRICT 6 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DISTRICT 7 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
DIST. 6 & 7 CROSS-DISTRICTS |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
TOTAL DIST. 6 & 7 |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
COUNTY-WIDE 2001 PARK BOND ALLOCATION |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
COUNTY-WIDE CROSS-DISTRICTS |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
TOTAL COUNTY-WIDE |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
2005 PARK BOND
MAJOR PARK DEV |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
NEIGHBORHOOD PARK DEV |  | 13000000 | 2972641.37 | 8213542.27 |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
ATHLETIC COMPLEX RENOV |  | 7000000 | 5940391.01 | 818455.66 |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
ARTS & CULTURE CENTER |  | 3250000 | 3174544.57 | 75325.43 |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
OTHER 2001 FUNDING |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
CROSS-DISTRICT 2005 PARKS BOND |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!
2005 PARK BOND TOTALS |  | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF! |  | #REF!

## 2005
DEKALB COUNTY GOVERNMENT
PARKS BOND FUND STATUS REPORT - 2006 PARKS BOND
January 2009
2006 PARKS BOND FUNDING - DEVELOPMENT
Project | DESCRIPTION |  | Budget | Actual Cost | Commitments* | Total Cost | Project Balance
101880 | MAJOR PARK DEV
50.1 | Brook Run Park |  | 11500000 | 4484927.77 | 51496.05 | 4536423.82 | 6963576.18
30.2 | Browns Mill Aquatic Center |  | 5937708.19 | 5658955.82 | 112612.68 | 5771568.5 | 166139.69
40.1 | Exchange Park |  | 8000000 | 349426.27 | 967211.73 | 1316638 | 6683362
7 | Gresham Park |  | 1000000 | 0 | 0 | 0 | 1000000
3.1 | Mason Mill Park |  | 2062291.78 | 75450.12 | 9001 | 84451.12 | 1977840.66
10.2 | Wade Walker Park |  | 11500000.4 | 651561.69 | 874894.33 | 1526456.02 | 9973544.38
10.2 | Reserve/Uncommitted |  | 210000 | 0 | 0 | 0 | 210000
| TOTAL MAJOR PARKS |  | 40210000.37 | 11220321.67 | 2015215.79 | 13235537.46 | 26974462.91
101881 | NEIGHBOR PARK DEV
6.2 | Arabia Mountain |  | 800000 | 731020.03 | 119446.55 | 850466.58 | -50466.58
9.1 | Buena Vista Park/Barker-Bryant |  | 600000 | 425939.55 | 180660.45 | 606600 | -6600
6.6 | Constitution Lakes |  | 400000 | 123370.3 | 48004.7 | 171375 | 228625
6.1 | Deepdene |  | 400000 | 410507.5 | 0 | 410507.5 | -10507.5
6.5 | Little Creek Horse Farm |  | 1000000 | 196020.82 | 688683.59 | 884704.41 | 115295.59
6.9 | Mystery Valley |  | 1300000 | 427598.24 | 0 | 427598.24 | 872401.76
7.1 | Redan Park |  | 6000000 | 608759.93 | 777021.07 | 1385781 | 4614219
6.1 | Sugar Creek Golf |  | 1300000 | 49425 | 0 | 49425 | 1250575
| Reserve/Uncommitted |  | 1200000 | 0 | 0 | 0 | 1200000
| TOTAL NEIGHBORHOOD PARKS |  | 13000000 | 2972641.37 | 1813816.36 | 4786457.73 | 8213542.27
101882 | ATHLETIC COMPLEX RENOVATION
1 | Management Services |  | 469350 | 385924.97 | 83425.03 | 469350 | 0
3 | Athletic Park Renovations |  | 2987800.1 | 1988691.16 | 114802.8 | 2103493.96 | 884306.14
3.1 | GA Power Contracts |  | 1905641 | 1862715.5 | 42925.5 | 1905641 | 0
3.2 | Dresden Park Phase II |  | 668309.9 | 734161.38 | 0 | 734161.38 | -65851.48
| Murphy Candler |  | 968899 | 968898 | 0 | 968898 | 1
3.3 | Reserve/Uncommitted |  | 0 | 0 | 0 | 0 | 0
| TOTAL ATHL COMPLEX RENOV |  | 7000000 | 5940391.01 | 241153.33 | 6181544.34 | 818455.66
101882 | DAM RENOVATIONS
1 | Buena Vista Park |  | 500000 | 443083.19 | 600.5 | 443683.69 | 56316.31
| Reserve/Uncommitted |  | 1500000 | 0 | 0 | 0 | 1500000
| TOTAL DAM RENOVATIONS |  | 2000000 | 443083.19 | 600.5 | 443683.69 | 1556316.31
101884 | ARTS & CULTURE CTR
3 | South Dekalb Art Center |  | 1500000 | 1500000 | 0 | 1500000 | 0
4 | Callanwolde |  | 1500000 | 1426425 | 0 | 1426425 | 73575
6.1 | Ashford Park Dev. |  | 250000 | 248119.57 | 130 | 248249.57 | 1750.43
| Reserve/Uncommitted |  | 0 | 0 | 0 | 0 | 0
| TOTAL ARTS & CULTURE CTR |  | 3250000 | 3174544.57 | 130 | 3174674.57 | 75325.43
BELTWAY PATH
| Miners Creek (Acquisition) |  | 155000 | 132517.39 | 0 | 132517.39 | 22482.61
| Intrenchment Creek (Acquisition) |  | 400000 | 315029 | 0 | 315029 | 84971
| Pedestrian Bridge |  | 1000000 | 0 | 0 | 0 | 1000000
| Bridge Design |  | 97418 | 73389.99 | 24028.01 | 97418 | 0
| Arabia Mountain Trails |  | 79460.26 | 79460.26 | 0 | 79460.26 | 0
| Perimeter Trail |  | 240778.5 | 240778.5 | 0 | 240778.5 | 0
| Reserve/Uncommitted |  | 1027343 | 0 | 0 | 0 | 1027343
| TOTAL BELTWAY PATH |  | 2999999.76 | 841175.14 | 24028.01 | 865203.15 | 2134796.61
2006 PARKS BOND FUNDING - ACQUISITIONS
LAND ACQUISITIONS
| Arabia Browns Mill |  | 4025000 | 4004935.9 | 0 | 4004935.9 | 20064.1
| Arabia Conservation Fund |  | 1885000 | 1883294.96 | 0 | 1883294.96 | 1705.04
| Arabia Klondike |  | 389000 | 374879.21 | 0 | 374879.21 | 14120.79
| Intrenchment Creek Connection |  | 400000 | 315028.25 | 0 | 315028.25 | 84971.75
| Twin Brothers Lakes |  | 1570000 | 1567876.42 | 0 | 1567876.42 | 2123.58
| Reserve/Uncommitted |  | 19731000 | 0 | 0 | 0 | 19731000
| TOTAL LAND ACQUISITIONS |  | 28000000 | 8146014.74 | 0 | 8146014.74 | 19853985.26
| 2006 PARKS BOND TOTAL |  | 96460000.13 | 32738171.69 | 4094943.99 | 36833115.68 | 59626884.45
101883 | DAM RENOVATIONS
1 | RESERVE |  | 1500000 | 0 |  |  | 1500000
2.1 | LAKE BUENA VISTA |  | 500000 | 867000 |  |  | -367000
| SUBTOTAL |  | 2000000 | 867000 |  |  | 1133000
101884 | ARTS & CULTURE CENTER
3 | SOUTH DEKALB ART CEN |  | 1500000 | 1500000 |  |  | 0
4 | CALLENWOLDE |  | 1500000 | 52771.1 |  |  | 1447228.9
6.1 | ASHFORD PARK DEV. |  | 650000 | 598111.24 |  |  | 51888.76
| SUBTOTAL |  | 3650000 | 2150882.34 |  |  | 1499117.66
BELTWAY PATH
1 | RESERVE |  | 1347582 | 90650.2 |  |  | 1256931.8
2 | ISSUANCE COSTS |  | 0 | 229588.59 |  |  | -229588.59
6.1 | PEDESTRIAN BRIDGE285 |  | 1000000 | 0 |  |  | 1000000
6.2 | BRIDGE DESIGN |  | 97418 | 97418 |  |  | 0
| SUBTOTAL |  | 2445000 | 417656.79 |  |  | 2027343.21
| TOTAL |  | #REF! | #REF! |  |  | #REF!
* Commitments represent the balance on any active contract (purchase order).

## Interest
DEKALB COUNTY GOVERNMENT
PARKS BOND FUND STATUS REPORT - 2006 PARKS BOND
January 2009
2006 PARKS BOND FUNDING - INTEREST
Project | DESCRIPTION |  | Budget | Actual Cost | Commitments2 | Total Cost | Project Balance
101880
50.1 | South Dekalb Arts and Culture Ctr |  | 2900000 | 1400000 | 0 | 1400000 | 1500000
30.2 | Project Management |  | 1377894.51 | 0 | 0 | 0 | 1377894.51
40.1 | Ashford Park |  | 400000 | 400000 | 0 | 400000 | 0
7 | Browns Mill Park |  | 607467.41 | 0 | 0 | 0 | 607467.41
| Ball Field Maintenance |  | 326400 | 0 | 0 | 0 | 326400
10.2 | Unallocated |  | 3974206.01 | 0 | 0 | 0 | 3974206.01
| TOTAL 2006 PARKS BOND INTEREST 1 |  | 9585967.93 | 1800000 | 0 | 1800000 | 7785967.93
101883 | DAM RENOVATIONS
1 | RESERVE |  | 1500000 | 0 |  |  | -1500000 | 1500000
2.1 | LAKE BUENA VISTA |  | 500000 | 867000 |  |  | -500000 | -367000
| SUBTOTAL |  | 2000000 | 867000 |  |  | -2000000 | 1133000
101884 | ARTS & CULTURE CENTER
3 | SOUTH DEKALB ART CEN |  | 1500000 | 1500000 |  |  | -1500000 | 0
4 | CALLENWOLDE |  | 1500000 | 52771.1 |  |  | -1500000 | 1447228.9
6.1 | ASHFORD PARK DEV. |  | 650000 | 598111.24 |  |  | -650000 | 51888.76
| SUBTOTAL |  | 3650000 | 2150882.34 |  |  | -3650000 | 1499117.66
BELTWAY PATH
1 | RESERVE |  | 1347582 | 90650.2 |  |  | -1347582 | 1256931.8
2 | ISSUANCE COSTS |  | 0 | 229588.59 |  |  | 0 | -229588.59
6.1 | PEDESTRIAN BRIDGE285 |  | 1000000 | 0 |  |  | -1000000 | 1000000
6.2 | BRIDGE DESIGN |  | 97418 | 97418 |  |  | -97418 | 0
| SUBTOTAL |  | 2445000 | 417656.79 |  |  | -2445000 | 2027343.21
| TOTAL |  | #REF! | #REF! |  |  | #REF! | #REF!
1 The total interest budget represents the appropriated interest, not interest earned.
2 Commitments represent the balance on any active contract (purchase order).

## 101880
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
70.1 | BROOK RUN DEMOLITION | 4317400 | 1915078.75 | 0 | 1915078.75 | 2402321.25 | 44
2 | BROOK RUN DEVELOP | 4824864 | 124982 | 0 | 124982 | 4699882 | 3
50.1 | BROOK RUN SKATE | 2357736 | 2444867.02 | 51496.05 | 2496363.07 | -138627.07 | 106
|  | 11500000 | 4484927.77 | 51496.05 | 4536423.82 | 6963576.18
6 | BROWNS MILL | 0 | 31596.11 | 0 | 31596.11 | -31596.11 | 0
30.2 | BROWN'S MILL | 393000 | 402950.11 | 35625.85 | 438575.96 | -45575.96 | 112
10.1 | BROWNS MILL CONST | 5544708.19 | 5224409.6 | 76986.83 | 5301396.43 | 243311.76 | 96
|  | 5937708.19 | 5658955.82 | 112612.68 | 5771568.5 | 166139.69
8 | EXCHANGE | 7270512 | 0 | 514000 | 514000 | 6756512 | 7
40.1 | EXCHANGE | 416988 | 267901.27 | 149086.73 | 416988 | 0 | 100
40.2 | Exchange Architec/En | 312500 | 81525 | 304125 | 385650 | -73150 | 123
|  | 8000000 | 349426.27 | 967211.73 | 1316638 | 6683362
7 | GRESHAM | 1000000 | 0 | 0 | 0 | 1000000 | 0
|  | 1000000 | 0 | 0 | 0 | 1000000
3 | MASON MILL | 2030291.78 | 43450.12 | 9001 | 52451.12 | 1977840.66 | 3
3.1 | TENNIS CENTER | 32000 | 32000 | 0 | 32000 | 0 | 100
|  | 2062291.78 | 75450.12 | 9001 | 84451.12 | 1977840.66
5 | WADE WALKER | 9110852 | 0 | 0 | 0 | 9110852 | 0
30.1 | WADE WALKER | 1505497.4 | 644061.69 | 874894.33 | 1518956.02 | -13458.62 | 101
10.2 | WADE WALKER -POTTS | 883650 | 7500 | 0 | 7500 | 876150 | 1
|  | 11499999.4 | 651561.69 | 874894.33 | 1526456.02 | 9973543.38
1 | RESERVE | 210000 | 0 | 0 | 0 | 210000 | 0
|  | 210000 | 0 | 0 | 0 | 210000
|  | 40209999.37 | 11220321.67 | 2015215.79 | 13235537.46 | 26974461.91

## 101881
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
6.2 | ARABIA MTN. | 800000 | 731020.03 | 119446.55 | 850466.58 | -50466.58 | 106
9.1 | BUENA VISTA PARK | 600000 | 425939.55 | 180660.45 | 606600 | -6600 | 101
6.6 | CONSTITUTION LKS | 400000 | 123370.3 | 48004.7 | 171375 | 228625 | 43
6.1 | DEEPDENE DRAINAGE | 400000 | 410507.5 | 0 | 410507.5 | -10507.5 | 103
6.3 | DRESDAN | 434440 | 0 | 0 | 0 | 434440 | 0
8.1 | DRESDEN FIELD | 65560 | 0 | 0 | 0 | 65560 | 0
6.5 | LITTLE CRK HORSE FRM | 1000000 | 196020.82 | 688683.59 | 884704.41 | 115295.59 | 88
6.9 | MYSTERY VAL PATH | 376356.64 | 34066.64 | 0 | 34066.64 | 342290 | 9
6.8 | MYSTERY VALLEY | 923643.36 | 393531.6 | 0 | 393531.6 | 530111.76 | 43
6.4 | REDAN | 5206405 | 290440.78 | 628225.22 | 918666 | 4287739 | 18
7.1 | REDAN RC | 467115 | 318319.15 | 148795.85 | 467115 | 0 | 100
6.1 | REDAN REC CENTR | 326480 | 0 | 0 | 0 | 326480 | 0
1 | RESERVE | 700000 | 0 | 0 | 0 | 700000 | 0
6.7 | SUGAR CRK GLF COURSE | 1300000 | 49425 | 0 | 49425 | 1250575 | 4
|  | 13000000 | 2972641.37 | 1813816.36 | 4786457.73 | 8213542.27

## 101882
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | MANAGEMENT SERVICES | 469350 | 385924.97 | 83425.03 | 469350 | 0 | 100
2 | ISSUANCE COSTS | 0 | 0 | 0 | 0 | 0 | 0
3 | ATHLETIC PRK RENOV | 2987800.1 | 1988691.16 | 114802.8 | 2103493.96 | 884306.14 | 70
3.1 | GA PWR CONTRACTS | 1905641 | 1862715.5 | 42925.5 | 1905641 | 0 | 100
3.2 | DRESDEN PARK PH II | 668309.9 | 734161.38 | 0 | 734161.38 | -65851.48 | 110
3.3 | MURPHY CANDLER GIRLS | 968899 | 968898 | 0 | 968898 | 1 | 100
|  | 7000000 | 5940391.01 | 241153.33 | 6181544.34 | 818455.66

## 101883
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 1500000 | 0 | 0 | 0 | 1500000 | 0
2.1 | LAKE BUENA VISTA | 500000 | 443083.19 | 600.5 | 443683.69 | 56316.31 | 89
|  | 2000000 | 443083.19 | 600.5 | 443683.69 | 1556316.31

## 101884
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 0 | 0 | 0 | 0 | 0 | 0
3 | SOUTH DEKALB ART CEN | 1500000 | 1500000 | 0 | 1500000 | 0 | 100
4 | CALLENWOLDE | 1500000 | 1426425 | 0 | 1426425 | 73575 | 95
6.1 | ASHFORD PARK DEV. | 400000 | 248119.57 | 130 | 248249.57 | 151750.43 | 62
|  | 3400000 | 3174544.57 | 130 | 3174674.57 | 225325.43
75325.43

## 101885
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 1347582 | 90650.2 | 0 | 90650.2 | 1256931.8 | 7
2 | ISSUANCE COSTS | 0 | 229588.59 | 0 | 229588.59 | -229588.59 | 0
5.1 | MINERS CREEK | 155000 | 132517.39 | 0 | 132517.39 | 22482.61 | 85
5.5 | INTRENCHMENT CREEK | 400000 | 315029 | 0 | 315029 | 84971 | 79
6.1 | PEDESTRIAN BRIDGE285 | 1000000 | 0 | 0 | 0 | 1000000 | 0
6.2 | BRIDGE DESIGN | 97418 | 73389.99 | 24028.01 | 97418 | 0 | 100
|  | 3000000 | 841175.17 | 24028.01 | 865203.18 | 2134796.82

## 101886
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
5.3 | ARABIA BROWN'S MILL | 4025000 | 4004935.9 | 0 | 4004935.9 | 20064.1 | 100
5.8 | ARABIA CONSERV FUND | 1885000 | 1883294.96 | 0 | 1883294.96 | 1705.04 | 100
5.2 | ARABIA KLONDIKE | 389000 | 374879.21 | 0 | 374879.21 | 14120.79 | 96
5.5 | INTRENCHMENT CRK CON | 400000 | 315028.25 | 0 | 315028.25 | 84971.75 | 79
2 | ISSUANCE COSTS | 0 | 0 | 0 | 0 | 0 | 0
5.7 | JOHNSON PROPERTY | 0 | 0 | 0 | 0 | 0 | 0
5.6 | LYONS-W&S | 0 | 0 | 0 | 0 | 0 | 0
5.4 | TWIN BROTHERS | 1570000 | 1567876.42 | 0 | 1567876.42 | 2123.58 | 100
1 | RESERVE | 19731000 | 0 | 0 | 0 | 19731000 | 0
|  | 28000000 | 8146014.74 | 0 | 8146014.74 | 19853985.26

## Other (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT - DETAIL
APRIL 2008
DRAFT
|  |  | INTEREST FUNDING |  |  | PROJECTIONS |  | OTHER BOND FUNDING
Project | DESCRIPTION |  | Total Allocated | Total Cost To Date | Project Balance | $ Estimate to Complete | Funding Needed | 2001 Other District(s) |  | 2001 CountyWide | 2005 | Interest Funding | Other | Total Funding
INTEREST 2001 PARK BOND
PROJECTS
101490 | Cty-Wide Little Horse-Dev |  | 150000 | 138521.36 | 11478.64 |  |  |  |  | 3865 | 1000000 |  |  | 1153865
101491 | Cty-Wide Reloc. Park Main-Dev |  | 100000 | 98902.56 | 1097.44 | [8 empty] | 100000
101492 | Cty-Wide P&R Mast. Plan-Dev |  | 275000 | 97700 | 177300 | [8 empty] | 275000
101493 | Cty-Wide Gen. Park Impr.-Dev |  | 495243.11 | 253699.66 | 241543.45 | [8 empty] | 495243.11
101943 | Cty-Wide High Prior Main-Dev |  | 752744.34 | 722898.04 | 29846.3 | [8 empty] | 752744.34
102179 | Cty-Wide Park Pools Repairs |  | 1033677 | 978372.16 | 55304.84 | [8 empty] | 1033677
| TOTAL 2001 PARK BOND INTEREST |  | 2806664.45 | 2290093.78 | 516570.67 | 0 | 0 | 0 | 0 | 3865 | 1000000 | 0 | 0 | 3810529.45
INTEREST 2005 PARK BOND
PROJECTS
101884 | Arts Cult Centers |  | 1400000 | 1400000 | 0 | [5 empty] | 1500000 |  |  | 2900000
102385 | Ball Field Maint Equipment |  | 326400 | 0 | 326400 | [8 empty] | 326400
| TOTAL 2005 PARK BOND INTEREST |  | 1726400 | 1400000 | 326400 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 3226400
| TOTAL PARK BOND INTEREST |  | 4533064.45 | 3690093.78 | 842970.67 |  |  | 0 | 0 | 3865 | 2500000 | 0 | 0 | 7036929.45
DUNWOODY NATURE CENTER
100493 | Cty-wide Main Land Development |  | 7560 | 7560 | 0 | [8 empty] | 7560
| TOTAL OMNI COMM DEV CORP |  | 7560 | 7560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7560
OMNI COMMUNITY DEV CORP PARK BONDS
101528 | Dist. 3-Glen Emerald Rock Dev. |  | 25000 | 0 | 25000 | [8 empty] | 25000
| TOTAL OMNI COMM DEV CORP |  | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
600310 | ARTHUR BLANK
PROJECTS
100180 | A Blank-Constitution Dev |  | 100000 | 96870.09 | 3129.91 | [8 empty] | 100000
100596 | Dist.3 Constitution Dev. |  | 30000 | 0 | 30000 | [8 empty] | 30000
101437 | Dist. 2-Briar-Armstrong Dev. |  | 75000 | 2250 | 72750 | [8 empty] | 75000
| TOTAL 2005 PARK BOND INTEREST |  | 205000 | 99120.09 | 105879.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000
| TOTAL ARTHUR BLANK |  | 230000 | 99120.09 | 130879.91 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 230000
CALLANWOLDE ART CENTER
101882 | Athl Complex Renovations |  | 1100000 | 29390 | 1070610 | [8 empty] | 1100000
| TOTAL CALLANWOLDE ART CENTER |  | 1100000 | 29390 | 1070610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100000
GA DCA BRIARWOOD
100521 | DCA Briarwood Rec Center |  | 10000 | 0 | 10000 | [8 empty] | 10000
| TOTAL GA DCA BRIARWOOD |  | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
GA DCA SHOAL CREEK
100522 | DCA Shoal Creek |  | 10000 | 0 | 10000 | [8 empty] | 10000
| TOTAL GA DCA SHOAL CREEK |  | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
GA FC-INVASIVE PLANTS
101611 | GA FC-Invasive Plants |  | 45000 | 0 | 45000 | [8 empty] | 45000
| TOTAL GA FC-INVASIVE PLANTS |  | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000
GA DCA BROOKRUN
PROJECTS
100692 | GA DCA Brookrun (CL-610) |  | 50000 | 0 | 50000 | [5 empty] | 0 |  |  | 50000
100693 | GA DCA Brookrun (CL-656) |  | 15000 | 0 | 15000 | [8 empty] | 15000
| TOTAL 2005 PARK BOND INTEREST |  | 65000 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000
SAFECO WADE WALKER PARK
100784 | SafeCo Wade Walker |  | 7500 | 0 | 7500 | [8 empty] | 7500
| TOTAL SAFECO WADE WALKER |  | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500
WALMART STORES
102383 | Walmart Stores |  | 50000 | 0 | 50000 | [8 empty] | 50000
| TOTAL WALMART STORES |  | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
WALMART FOUNDATION
101972 | Walmart Foundation |  | 2000 | 1200 | 800 | [8 empty] | 2000
| TOTAL WALMART FOUNDATION |  | 2000 | 1200 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000

## MajorPkDev 101880 (hidden)
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 210000 | 0 | 0 | 0 | 210000 | 0
2 | BROOK RUN DEVELOP | 4824864 | 124982 | 0 | 124982 | 4699882 | 3
3 | MASON MILL | 2030291.78 | 29950.12 | 1 | 29951.12 | 2000340.66 | 1
5 | WADE WALKER | 9110852 | 0 | 0 | 0 | 9110852 | 0
6 | BROWNS MILL | 0 | 0 | 0 | 0 | 0 | 0
7 | GRESHAM | 1000000 | 0 | 0 | 0 | 1000000 | 0
8 | EXCHANGE | 7270512 | 0 | 514000 | 514000 | 6756512 | 7
10.1 | BROWNS MILL CONST | 5544708.19 | 4924282.18 | 544326.93 | 5468609.11 | 76099.08 | 99
10.2 | WADE WALKER -POTTS | 883650 | 7500 | 0 | 7500 | 876150 | 1
3.1 | TENNIS CENTER | 32000 | 32000 | 0 | 32000 | 0 | 100
30.1 | WADE WALKER | 1505497.4 | 620270.62 | 898685.4 | 1518956.02 | -13458.62 | 101
30.2 | BROWN'S MILL | 950467.41 | 400286.15 | 34800.85 | 435087 | 515380.41 | 46
40.1 | EXCHANGE | 416988 | 217236 | 199752 | 416988 | 0 | 100
40.2 | Exchange Architec/En | 312500 | 0 | 312500 | 312500 | 0 | 100
50.1 | BROOK RUN SKATE | 2357736 | 209754.48 | 51496.05 | 261250.53 | 2096485.47 | 11
70.1 | DEMOLITION BROOK RUN | 4317400 | 4023240.04 | 99765.25 | 4123005.29 | 194394.71 | 95
| TOTAL | 40767466.78 | 10589501.59 | 2655327.48 | 13244829.07 | 27522637.71

## District1 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 1
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 1
100571 | DIST.1 BROOK RUN DEV. |  | 2220400 | 2108636.71 | 111763.29
100572 | DIST.1 DEVELOPMENT.DEV |  | 1603017.97 | 258135.97 | 1344882
100573 | DIST.1 SPEC PROJ. DEV. |  | 164198 | 53952 | 110246
100575 | DIST.1 PROF. SERVICES DEV. |  | 25402 | 16536.86 | 8865.14
101691 | DIST1 CAND MURPH PRK |  | 200000 | 60359.51 | 139640.49
102160 | DIST. 1 DUNWOODY NATURE CENTER |  | 60000 | 27194.95 | 32805.05
| TOTAL |  | 4273017.97 | 2524816 | 1748201.97 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## District2 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 2
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 2
100581 | DIST.2 LAVISTA PARK DEV. |  | 435893 | 66049.96 | 369843.04
100582 | DIST.2 BRIARWOOD DEV. |  | 120000 | 0 | 120000
100583 | DIST.2 CONSULT. SERV. DEV. |  | 105000 | 70000 | 35000
100584 | DIST.2 CONSULTING DRES.DEV. |  | 1489154 | 1489154 | 0
100585 | DIST.2 DEVELOPMENT |  | 1172124.97 | 55882.87 | 1116242.1
100586 | DIST.2 OLMSTEAD DEV. |  | 500000 | 500000 | 0
100587 | DIST.2 PARKSIDE PARK DEV. |  | 35000 | 0 | 35000
100588 | DIST.2 SPEC. PROJECTS DEV. |  | 846 | 149.5 | 696.5
101137 | MASON MILL DOG PARK |  | 20000 | 19830.22 | 169.78
102159 | DIST. 2 OLMSTEAD-DEEPDENE |  | 400000 | 400000 | 0
| TOTAL |  | 4278017.97 | 2601066.55 | 1676951.42 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## District3 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 3
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 3
100570 | DIST. 3 DEARBORN PARK DEV. |  | 12000 | 0 | 12000
100596 | DIST.3 CONSTITUTION DEV. |  | 140000 | 139787.74 | 212.26
100597 | DIST.3 CONSULTING DEV. |  | 35000 | 35000 | 0
100598 | DIST.3 DEKALB MEMORIAL DEV. |  | 28000 | 0 | 28000
100599 | DIST.3 DEVELOPMENT DEV. |  | 81925.97 | 21430 | 60495.97
100600 | DIST.3 EXCHANGE PARK DEV. |  | 254400 | 19225 | 235175
100601 | DIST.3 GRESHAM PARK DEV. |  | 943000 | 108746.66 | 834253.34
100602 | DIST.3 LONGDALE PARK DEV. |  | 65700 | 61700 | 4000
100603 | DIST.3 NH SCOTT(MARK TRL) DEV. |  | 1000000 | 241843.48 | 758156.52
100604 | DIST.3 MIDWAY PARK DEV. |  | 239400 | 0 | 239400
100605 | DIST.3 PARK DESIGN DEV. |  | 511960 | 40035.81 | 471924.19
100606 | DIST.3 SHOAL CREEK 2 DEV. |  | 60000 | 2120 | 57880
100607 | DIST.3 SHOAL CREEK DEV. |  | 30000 | 0 | 30000
100608 | DIST.3 SPEC. PROJ. DEV. |  | 126520 | 13226.9 | 113293.1
100609 | DIST.3 SUMMERGATE DEV. |  | 490112 | 479133.15 | 10978.85
101175 | DIST.3 MEM./DOG PARK.DEV |  | 35000 | 0 | 35000
101528 | DIST.3-GLEN EMER.ROCK-DEV |  | 125000 | 26852 | 98148
101692 | DIST.3-RAINBOW.DEV |  | 100000 | 2276.56 | 97723.44
| TOTAL |  | 4278017.97 | 1191377.3 | 3086640.67 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## District4 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 4
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 4
100619 | DIST.4 HIDDEN ACRES DEV. |  | 460600 | 377584.83 | 83015.17
100620 | DIST.4 SPEC PROJ DEV. |  | 66198 | 9511.06 | 56686.94
100621 | DIST 4 OAK CREEK.DEV |  | 28202 | 23873.07 | 4328.93
100622 | DIST.4 TOBIE GRANT DEV. |  | 35000 | 7500 | 27500
100623 | DIST.4 WADE WALKER DEV. |  | 2536772 | 2523758.03 | 13013.97
100655 | DISTRICT 4 DEVELOPMENT |  | 1151245.97 | 5952 | 1145293.97
| TOTAL |  | 4278017.97 | 2948178.99 | 1329838.98 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## District5 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 5
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 5
100096 | DIST.5-DEVELOPMENT |  | 35000 | 22170 | 12830
100104 | DIST.5- SPECIAL PROJ DEV |  | 101027.97 | 20983.35 | 80044.62
100105 | DIST.5- BOULDERCREST DEV |  | 73380 | 53997.07 | 19382.93
100107 | DIST.5- BROWNSMILL DEV |  | 2312250 | 2304560.55 | 7689.45
100110 | DIST.5- ARABIA ALLIANCE DEV |  | 750000 | 750000 | 0
100116 | DIST.5- COMP DEV REDAN DEV |  | 750000 | 12100 | 737900
100117 | DIST.5-ROCK CHAPEL PARK DEV |  | 250000 | 1792 | 248208
100118 | DIST.5-SALEM PARK DEV |  | 6360 | 5460 | 900
| TOTAL |  | 4278017.97 | 3171062.97 | 1106955 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## District6 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 6
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 6
100126 | DIST.6-DEVLOPMENT |  | 300000 | 300000 | 0
100129 | DIST.6-SPECIALPROJ DEV |  | 15000 | 15000 | 0
100130 | DIST.6-ASHFORD PARK DEV |  | 125000 | 142445.67 | -17445.67
100131 | DIST.6-BRIARWOOD REC DEV |  | 120000 | 0 | 120000
100135 | DIST.6-DRESDEN PARK DEV |  | 300000 | 273139.75 | 26860.25
100137 | DIST.6-DUNWOODY NAT CNTR DEV |  | 125000 | 125000 | 0
100139 | DIST.6-KITTREDGE PRK DEV |  | 400000 | 0 | 400000
100140 | DIST.6-LYNWOOD PARK RENO DEV |  | 200000 | 37600 | 162400
100141 | DIST.6-MEDLOCK PARK DEV |  | 225117.98 | 151926.31 | 73191.67
100142 | DIST.6-MURPH CANDLER PRK DEV |  | 175000 | 160393.26 | 14606.74
100144 | DIST.6-BROOK RUN DEV |  | 400000 | 400075.69 | -75.69
100145 | DIST.6-ARMSTRONG PRK DEV |  | 100000 | 64498.86 | 35501.14
100147 | DIST.6-BOULDERCREST DEV |  | 264000 | 207891.69 | 56108.31
100149 | DIST.6-FORK CRK MT PARK DEV |  | 200000 | 0 | 200000
100150 | DIST.6-HAMILTON PARK DEV |  | 400000 | 303043.54 | 96956.46
100151 | DIST.6-GOLF COURSE IMP DEV |  | 378000 | 163628.54 | 214371.46
100152 | DIST.6-DEEPENE PRK DEV |  | 5900 | 5900 | 0
100154 | DIST.6-INTRENCHMENT CRK DEV |  | 110000 | 0 | 110000
100156 | DIST.6-CONSTITUTION LAKES DEV |  | 40000 | 30265 | 9735
100172 | DIST.6-SAGAMORE DEV |  | 100000 | 0 | 100000
101353 | DIST.6 #03-9426 OLMSTEAD. DEV. |  | 150000 | 150000 | 0
101501 | DIST.6-BROOK RUN THEATRE |  | 145000 | 0 | 145000
| TOTAL |  | 4278017.98 | 2530808.31 | 1747209.67 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## District7 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
2001 PARK BOND FUND - DISTRICT 7
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
DISTRICT 7
100173 | DIST.7-DEVELOPMENT |  | 822538.37 | 5000 | 817538.37
100174 | DIST.7-SPECIAL PROJ DEV |  | 57149.6 | 19248.1 | 37901.5
100176 | DIST.7-MEADOWDALE PRK DEV |  | 701953 | 655913.4 | 46039.6
100177 | DIST.7-FLAT SHOALS DEV |  | 1205000 | 289178.17 | 915821.83
100178 | DIST.7-BIFFLE PARK DEV |  | 680420 | 604338 | 76082
100179 | DIST.7-PETERS PARK DEV |  | 410957 | 407781.6 | 3175.4
101680 | DIST 7 ARAB MT.BIKE.DEV |  | 300000 | 300000 | 0
102081 | DIST. 7 SALEM PARK |  | 100000 | 0 | 100000
| TOTAL |  | 4278017.97 | 2281459.27 | 1996558.7 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## NeighPkDev 101881 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
2005 PARK BOND FUND
101881 | NEIGHBOR PARK DEVELOPMENT
1 | RESERVE |  | 700000 | 0 | 700000
6.1 | DEEPDENE DRAINAGE |  | 400000 | 400000 | 0
6.1 | REDAN REC CENTR |  | 326480 | 0 | 326480
6.2 | ARABIA MTN. |  | 800000 | 850466.58 | -50466.58
6.3 | DRESDAN |  | 434440 | 0 | 434440
6.4 | REDAN |  | 5206405 | 918666 | 4287739
6.5 | LITTLE CRK HORSE FRM |  | 1000000 | 1 | 999999
6.6 | CONSTITUTION LKS |  | 400000 | 287210 | 112790
6.7 | SUGAR CRK GLF COURSE |  | 1300000 | 49425 | 1250575
6.8 | MYSTERY VALLEY |  | 923643.36 | 393531.6 | 530111.76
6.9 | MYSTERY VAL PATH |  | 376356.64 | 34066.64 | 342290
7.1 | REDAN RC |  | 467115 | 467115 | 0
8.1 | DRESDEN FIELD |  | 65560 | 65560 | 0
9.1 | BUENA VISTA PARK |  | 600000 | 600000 | 0
| TOTAL |  | 13000000 | 4066041.82 | 8933958.18 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## AthlCmpxRevov 101882 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
2005 PARK BOND FUND
101882 | ATHLETIC COMPLEX RENOV
1 | MANAGEMENT SERVICES |  | 469350 | 469350 | 0
2 | ISSUANCE COSTS |  | 0 | 237000 | -237000
3 | ATHLETIC PRK RENOV |  | 2987800.1 | 777034.8 | 2210765.3
3.1 | GA PWR CONTRACTS |  | 1905641 | 0 | 1905641
3.2 | DRESDEN PARK PH II |  | 668309.9 | 671359.4 | -3049.5
3.3 | MURPHY CANDLER GIRLS |  | 968899 | 968898 | 1
| TOTAL |  | 7000000 | 3123642.2 | 3876357.8 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## DamRev 101883 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
2005 PARK BOND FUND
101883 | DAM RENOVATIONS
1 | RESERVE |  | 1500000 | 0 | 1500000
2.1 | LAKE BUENA VISTA |  | 500000 | 867000 | -367000
| TOTAL |  | 2000000 | 867000 | 1133000 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## ArtCult 101884 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
2005 PARK BOND FUND
101884 | ARTS & CULTURE CENTER
3 | SOUTH DEKALB ART CEN |  | 1500000 | 1500000 | 0
4 | CALLENWOLDE |  | 1500000 | 52771.1 | 1447228.9
6.1 | ASHFORD PARK DEV. |  | 650000 | 598111.24 | 51888.76
| TOTAL |  | 3650000 | 2150882.34 | 1499117.66 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## PATH 101885 (hidden)
DEKALB COUNTY GOVERNMENT
PARK BOND FUND STATUS REPORT
APRIL 2008
DRAFT
|  |  | ACTUALS |  |  | PROJECTIONS
Project | Project Name |  | Budget | Total Cost To Date | Available Balance | $ Estimate to Complete | Funding Needed
2005 PARK BOND FUND
BELTWAY PATH
1 | RESERVE |  | 1347582 | 90650.2 | 1256931.8
2 | ISSUANCE COSTS |  | 0 | 229588.59 | -229588.59
6.1 | PEDESTRIAN BRIDGE285 |  | 1000000 | 0 | 1000000
6.2 | BRIDGE DESIGN |  | 97418 | 97418 | 0
| TOTAL |  | 2445000 | 417656.79 | 2027343.21 | 0 | 0
ADDITIONAL FUNDING JUSTIFICATION
DISTRICT NARRATIVE

## 600018 Countywide (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100484 | CTY- WIDE DEK MEM PK DEV. | 4761.28 | 4761.28 | 0 | 4761.28 | 0 | 100
100485 | CTY- WIDE POOL MDWY PK DEV. | 22718.34 | 22718.34 | 0 | 22718.34 | 0 | 100
100486 | CTY- WIDE POOL REN KIT PK DEV. | 8241.87 | 8241.87 | 0 | 8241.87 | 0 | 100
100487 | CTY- WIDE POOL REN MK TRL DEV. | 9921.52 | 9921.52 | 0 | 9921.52 | 0 | 100
100488 | CTY- WIDE POOL REN. TOBIE DEV. | 1983.63 | 1983.63 | 0 | 1983.63 | 0 | 100
100489 | CTY- WIDE TENNIS CEN DEV. | 345563.86 | 315606.36 | 29957.5 | 345563.86 | 0 | 100
100490 | CTY- WIDE TUCKER REC. CTR.DEV. | 11321.18 | 11321.18 | 0 | 11321.18 | 0 | 100
100491 | CTY-WIDE BRK RUN / VET MEM DEV | 137658.35 | 137658.35 | 0 | 137658.35 | 0 | 100
100493 | CTY-WIDE MAIN LAND DEVELOPMENT | 8134794.98 | 7500663.19 | 584040.08 | 8084703.27 | 50091.71 | 99
100494 | CTY-WIDE POOL REN LITH PK DEV. | 23246.06 | 23246.06 | 0 | 23246.06 | 0 | 100
100495 | CTY-WIDE POOL REN LYNWD PK DEV | 1612.41 | 1612.41 | 0 | 1612.41 | 0 | 100
100496 | CTY-WIDE POOL REN M .CAND DEV. | 187775.23 | 187775.23 | 0 | 187775.23 | 0 | 100
100497 | CTY-WIDE POOL REN MEDLK PK DEV | 28919.6 | 28919.6 | 0 | 28919.6 | 0 | 100
100498 | CTY-WIDE POOL RENV BRI WD DEV. | 50115 | 50115 | 0 | 50115 | 0 | 100
100499 | CTY-WIDE POOL RENV COF PK DEV. | 7111.12 | 7111.12 | 0 | 7111.12 | 0 | 100
100500 | CTY-WIDE POOL RENV GRSH PK DEV | 13606.78 | 13606.78 | 0 | 13606.78 | 0 | 100
100501 | CTY-WIDE TRUE LOVE ATLET. DEV. | 17331 | 17331 | 0 | 17331 | 0 | 100
100504 | CTY-WIDE-WADE WALKER DEV. | 216520 | 267879.59 | 0 | 267879.59 | -51359.59 | 124
101490 | CTY-WIDE LITTLE HORSE-DEV | 3865 | 2257 | 0 | 2257 | 1608 | 58
101491 | CTY-WIDE RELOC.PARK MAIN-DEV | 0 | 0 | 0 | 0 | 0
101492 | CTY-WIDE-P&R MAST.PLAN-DEV | 0 | 0 | 0 | 0 | 0
101493 | CTY-WIDE GEN.PARK IMPR.-DEV | 10960.89 | 10577.44 | 0 | 10577.44 | 383.45 | 97
101977 | CHAPEL HILL PARK DEV | 500000 | 57000 | 5627 | 62627 | 437373 | 13
|  | 9738028.1 | 8680306.95 | 619624.58 | 9299931.53 | 438096.57

## 600019 Distr1 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100571 | DIST.1 BROOK RUN DEV. | 2220400 | 1759490.61 | 349146.1 | 2108636.71 | 111763.29 | 95
100572 | DIST.1 DEVELOPMENT.DEV | 1603017.97 | 54973.62 | 203162.35 | 258135.97 | 1344882 | 16
100573 | DIST.1 SPEC PROJ. DEV. | 164198 | 34792.63 | 19159.37 | 53952 | 110246 | 33
100575 | DIST.1 PROF. SERVICES DEV. | 25402 | 16536.86 | 0 | 16536.86 | 8865.14 | 65
101691 | DIST1 CAND MURPH PRK | 200000 | 48796.14 | 11563.37 | 60359.51 | 139640.49 | 30
102160 | DIST. 1 DUNWOODY NATURE CENTER | 60000 | 15637.88 | 11557.07 | 27194.95 | 32805.05 | 45
|  | 4273017.97 | 1930227.74 | 594588.26 | 2524816 | 1748201.97

## 600020 Distr2 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100581 | DIST.2 LAVISTA PARK DEV. | 435893 | 60536.71 | 5513.25 | 66049.96 | 369843.04 | 15
100582 | DIST.2 BRIARWOOD DEV. | 120000 | 0 | 0 | 0 | 120000 | 0
100583 | DIST.2 CONSULT. SERV. DEV. | 105000 | 70000 | 0 | 70000 | 35000 | 67
100584 | DIST.2 CONSULTING DRES.DEV. | 1489154 | 1488919 | 235 | 1489154 | 0 | 100
100585 | DIST.2 DEVELOPMENT | 1172124.97 | 37574.76 | 18308.11 | 55882.87 | 1116242.1 | 5
100586 | DIST.2 OLMSTEAD DEV. | 500000 | 500000 | 0 | 500000 | 0 | 100
100587 | DIST.2 PARKSIDE PARK DEV. | 35000 | 0 | 0 | 0 | 35000 | 0
100588 | DIST.2 SPEC. PROJECTS DEV. | 846 | 0 | 149.5 | 149.5 | 696.5 | 18
101137 | MASON MILL DOG PARK | 20000 | 18576 | 1254.22 | 19830.22 | 169.78 | 99
102159 | DIST. 2 OLMSTEAD-DEEPDENE | 400000 | 400000 | 0 | 400000 | 0 | 100
|  | 4278017.97 | 2575606.47 | 25460.08 | 2601066.55 | 1676951.42

## 600650 YR2005 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
101875 | RESERVE AND CONTINGENCY | 579622.63 | 107254.17 | 0 | 107254.17 | 472368.46 | 19
101880 | MAJ PARK DEV PRGM | 40767466.78 | 10589501.59 | 2655327.48 | 13244829.07 | 27522637.71 | 32
101881 | NEIG PRK DV PRG | 13000000 | 2135642.98 | 1930398.84 | 4066041.82 | 8933958.18 | 31
101882 | ATHL COMPLX RENV | 7000000 | 2614035.62 | 509606.58 | 3123642.2 | 3876357.8 | 45
101883 | DAM RENOVATIONS | 2000000 | 420837.13 | 446162.87 | 867000 | 1133000 | 43
101884 | ARTS CULT CNTRS | 3650000 | 1535196.24 | 615686.1 | 2150882.34 | 1499117.66 | 59
101885 | PH.IV BELTWY PATH | 3000000 | 784850.68 | 76568.3 | 861418.98 | 2138581.02 | 29
101886 | LAND ACQUIS.PROJECTS | 28000000 | 6269219.78 | 0 | 6269219.78 | 21730780.22 | 22
|  | 97997089.41 | 24456538.19 | 6233750.17 | 30690288.36 | 67306801.05

## NeigPkDev 101881 (hidden)
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 700000 | 0 | 0 | 0 | 700000 | 0
6.1 | DEEPDENE DRAINAGE | 400000 | 400000 | 0 | 400000 | 0 | 100
6.1 | REDAN REC CENTR | 326480 | 0 | 0 | 0 | 326480 | 0
6.2 | ARABIA MTN. | 800000 | 697767.09 | 152699.49 | 850466.58 | -50466.58 | 106
6.3 | DRESDAN | 434440 | 0 | 0 | 0 | 434440 | 0
6.4 | REDAN | 5206405 | 172298.92 | 746367.08 | 918666 | 4287739 | 18
6.5 | LITTLE CRK HORSE FRM | 1000000 | 0 | 1 | 1 | 999999 | 0
6.6 | CONSTITUTION LKS | 400000 | 0 | 287210 | 287210 | 112790 | 72
6.7 | SUGAR CRK GLF COURSE | 1300000 | 49425 | 0 | 49425 | 1250575 | 4
6.8 | MYSTERY VALLEY | 923643.36 | 393531.6 | 0 | 393531.6 | 530111.76 | 43
6.9 | MYSTERY VAL PATH | 376356.64 | 34066.64 | 0 | 34066.64 | 342290 | 9
7.1 | REDAN RC | 467115 | 247519.49 | 219595.51 | 467115 | 0 | 100
8.1 | DRESDEN FIELD | 65560 | 60534.24 | 5025.76 | 65560 | 0 | 100
9.1 | BUENA VISTA PARK | 600000 | 80500 | 519500 | 600000 | 0 | 100
|  | 13000000 | 2135642.98 | 1930398.84 | 4066041.82 | 8933958.18

## AthCompx 101882 (hidden)
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | MANAGEMENT SERVICES | 469350 | 342095.18 | 127254.82 | 469350 | 0 | 100
2 | ISSUANCE COSTS | 0 | 202770 | 34230 | 237000 | -237000 | 0
3 | ATHLETIC PRK RENOV | 2987800.1 | 769519.96 | 7514.84 | 777034.8 | 2210765.3 | 26
3.1 | GA PWR CONTRACTS | 1905641 | 0 | 0 | 0 | 1905641 | 0
3.2 | DRESDEN PARK PH II | 668309.9 | 640097.9 | 31261.5 | 671359.4 | -3049.5 | 100
3.3 | MURPHY CANDLER GIRLS | 968899 | 659552.58 | 309345.42 | 968898 | 1 | 100
|  | 7000000 | 2614035.62 | 509606.58 | 3123642.2 | 3876357.8

## DamRenv 101883 (hidden)
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 1500000 | 0 | 0 | 0 | 1500000 | 0
2.1 | LAKE BUENA VISTA | 500000 | 420837.13 | 446162.87 | 867000 | -367000 | 173
|  | 2000000 | 420837.13 | 446162.87 | 867000 | 1133000

## Arts&Cult 101884 (hidden)
Task | Task Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
1 | RESERVE | 0 | 0 | 0 | 0 | 0 | 0
3 | SOUTH DEKALB ART CEN | 1500000 | 1500000 | 0 | 1500000 | 0 | 100
4 | CALLENWOLDE | 1500000 | 26425 | 26346.1 | 52771.1 | 1447228.9 | 4
6.1 | ASHFORD PARK DEV. | 650000 | 8771.24 | 589340 | 598111.24 | 51888.76 | 92
|  | 3650000 | 1535196.24 | 615686.1 | 2150882.34 | 1499117.66

## 600021 Distr3 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100570 | DIST. 3 DEARBORN PARK DEV. | 12000 | 0 | 0 | 0 | 12000 | 0
100596 | DIST.3 CONSTITUTION DEV. | 140000 | 139787.74 | 0 | 139787.74 | 212.26 | 100
100597 | DIST.3 CONSULTING DEV. | 35000 | 35000 | 0 | 35000 | 0 | 100
100598 | DIST.3 DEKALB MEMORIAL DEV. | 28000 | 0 | 0 | 0 | 28000 | 0
100599 | DIST.3 DEVELOPMENT DEV. | 81925.97 | 1430 | 20000 | 21430 | 60495.97 | 26
100600 | DIST.3 EXCHANGE PARK DEV. | 254400 | 19225 | 0 | 19225 | 235175 | 8
100601 | DIST.3 GRESHAM PARK DEV. | 943000 | 73835.59 | 34911.07 | 108746.66 | 834253.34 | 12
100602 | DIST.3 LONGDALE PARK DEV. | 65700 | 61700 | 0 | 61700 | 4000 | 94
100603 | DIST.3 NH SCOTT(MARK TRL) DEV. | 1000000 | 29695.78 | 212147.7 | 241843.48 | 758156.52 | 24
100604 | DIST.3 MIDWAY PARK DEV. | 239400 | 0 | 0 | 0 | 239400 | 0
100605 | DIST.3 PARK DESIGN DEV. | 511960 | 40035.81 | 0 | 40035.81 | 471924.19 | 8
100606 | DIST.3 SHOAL CREEK 2 DEV. | 60000 | 2120 | 0 | 2120 | 57880 | 4
100607 | DIST.3 SHOAL CREEK DEV. | 30000 | 0 | 0 | 0 | 30000 | 0
100608 | DIST.3 SPEC. PROJ. DEV. | 126520 | 13226.9 | 0 | 13226.9 | 113293.1 | 10
100609 | DIST.3 SUMMERGATE DEV. | 490112 | 479133.15 | 0 | 479133.15 | 10978.85 | 98
101175 | DIST.3 MEM./DOG PARK.DEV | 35000 | 0 | 0 | 0 | 35000 | 0
101528 | DIST.3-GLEN EMER.ROCK-DEV | 125000 | 26832 | 20 | 26852 | 98148 | 21
101692 | DIST.3-RAINBOW.DEV | 100000 | 2276.56 | 0 | 2276.56 | 97723.44 | 2
|  | 4278017.97 | 924298.53 | 267078.77 | 1191377.3 | 3086640.67

## 600022 Distr4 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100619 | DIST.4 HIDDEN ACRES DEV. | 460600 | 377584.83 | 0 | 377584.83 | 83015.17 | 82
100620 | DIST.4 SPEC PROJ DEV. | 66198 | 5959.06 | 3552 | 9511.06 | 56686.94 | 14
100621 | DIST 4 OAK CREEK.DEV | 28202 | 23873.07 | 0 | 23873.07 | 4328.93 | 85
100622 | DIST.4 TOBIE GRANT DEV. | 35000 | 7500 | 0 | 7500 | 27500 | 21
100623 | DIST.4 WADE WALKER DEV. | 2536772 | 2505532.33 | 18225.7 | 2523758.03 | 13013.97 | 99
100655 | DISTRICT 4 DEVELOPMENT | 1151245.97 | 5952 | 0 | 5952 | 1145293.97 | 1
|  | 4278017.97 | 2926401.29 | 21777.7 | 2948178.99 | 1329838.98

## 600307 Distr5 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100096 | DIST.5-DEVELOPMENT | 35000 | 22170 | 0 | 22170 | 12830 | 63
100104 | DIST.5- SPECIAL PROJ DEV | 101027.97 | 20983.35 | 0 | 20983.35 | 80044.62 | 21
100105 | DIST.5- BOULDERCREST DEV | 73380 | 53997.07 | 0 | 53997.07 | 19382.93 | 74
100107 | DIST.5- BROWNSMILL DEV | 2312250 | 2201482.33 | 103078.22 | 2304560.55 | 7689.45 | 100
100110 | DIST.5- ARABIA ALLIANCE DEV | 750000 | 714072.74 | 35927.26 | 750000 | 0 | 100
100116 | DIST.5- COMP DEV REDAN DEV | 750000 | 12100 | 0 | 12100 | 737900 | 2
100117 | DIST.5-ROCK CHAPEL PARK DEV | 250000 | 1792 | 0 | 1792 | 248208 | 1
100118 | DIST.5-SALEM PARK DEV | 6360 | 5460 | 0 | 5460 | 900 | 86
|  | 4278017.97 | 3032057.49 | 139005.48 | 3171062.97 | 1106955

## 600308 Distr6 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100126 | DIST.6-DEVLOPMENT | 300000 | 104531.94 | 195468.06 | 300000 | 0 | 100
100129 | DIST.6-SPECIALPROJ DEV | 15000 | 15000 | 0 | 15000 | 0 | 100
100130 | DIST.6-ASHFORD PARK DEV | 125000 | 132425.07 | 10020.6 | 142445.67 | -17445.67 | 114
100131 | DIST.6-BRIARWOOD REC DEV | 120000 | 0 | 0 | 0 | 120000 | 0
100135 | DIST.6-DRESDEN PARK DEV | 300000 | 268523.75 | 4616 | 273139.75 | 26860.25 | 91
100137 | DIST.6-DUNWOODY NAT CNTR DEV | 125000 | 79939.81 | 45060.19 | 125000 | 0 | 100
100139 | DIST.6-KITTREDGE PRK DEV | 400000 | 0 | 0 | 0 | 400000 | 0
100140 | DIST.6-LYNWOOD PARK RENO DEV | 200000 | 37600 | 0 | 37600 | 162400 | 19
100141 | DIST.6-MEDLOCK PARK DEV | 225117.98 | 133901.86 | 18024.45 | 151926.31 | 73191.67 | 67
100142 | DIST.6-MURPH CANDLER PRK DEV | 175000 | 160393.26 | 0 | 160393.26 | 14606.74 | 92
100144 | DIST.6-BROOK RUN DEV | 400000 | 400075.69 | 0 | 400075.69 | -75.69 | 100
100145 | DIST.6-ARMSTRONG PRK DEV | 100000 | 63248.86 | 1250 | 64498.86 | 35501.14 | 64
100147 | DIST.6-BOULDERCREST DEV | 264000 | 207891.69 | 0 | 207891.69 | 56108.31 | 79
100149 | DIST.6-FORK CRK MT PARK DEV | 200000 | 0 | 0 | 0 | 200000 | 0
100150 | DIST.6-HAMILTON PARK DEV | 400000 | 303043.54 | 0 | 303043.54 | 96956.46 | 76
100151 | DIST.6-GOLF COURSE IMP DEV | 378000 | 101475.9 | 62152.64 | 163628.54 | 214371.46 | 43
100152 | DIST.6-DEEPENE PRK DEV | 5900 | 5900 | 0 | 5900 | 0 | 100
100154 | DIST.6-INTRENCHMENT CRK DEV | 110000 | 0 | 0 | 0 | 110000 | 0
100156 | DIST.6-CONSTITUTION LAKES DEV | 40000 | 30265 | 0 | 30265 | 9735 | 76
100172 | DIST.6-SAGAMORE DEV | 100000 | 0 | 0 | 0 | 100000 | 0
101353 | DIST.6 #03-9426 OLMSTEAD. DEV. | 150000 | 150000 | 0 | 150000 | 0 | 100
101501 | DIST.6-BROOK RUN THEATRE | 145000 | 0 | 0 | 0 | 145000 | 0
|  | 4278017.98 | 2194216.37 | 336591.94 | 2530808.31 | 1747209.67

## 600309 Distr7 (hidden)
Project | Project Name | Budget | Actual Cost | Commitment Amt | Total Cost | Available Balance | % Complete
100173 | DIST.7-DEVELOPMENT | 822538.37 | 5000 | 0 | 5000 | 817538.37 | 1
100174 | DIST.7-SPECIAL PROJ DEV | 57149.6 | 19248.1 | 0 | 19248.1 | 37901.5 | 34
100176 | DIST.7-MEADOWDALE PRK DEV | 701953 | 627202.83 | 28710.57 | 655913.4 | 46039.6 | 93
100177 | DIST.7-FLAT SHOALS DEV | 1205000 | 187915.82 | 101262.35 | 289178.17 | 915821.83 | 24
100178 | DIST.7-BIFFLE PARK DEV | 680420 | 604338 | 0 | 604338 | 76082 | 89
100179 | DIST.7-PETERS PARK DEV | 410957 | 368565.36 | 39216.24 | 407781.6 | 3175.4 | 99
101680 | DIST 7 ARAB MT.BIKE.DEV | 300000 | 300000 | 0 | 300000 | 0 | 100
102081 | DIST. 7 SALEM PARK | 100000 | 0 | 0 | 0 | 100000 | 0
|  | 4278017.97 | 2112270.11 | 169189.16 | 2281459.27 | 1996558.7